## 2 Year Plan
Legend | Faith Formation |  |  | Worship |  |  | Governance and Operations | [5 empty] | Justice and Community Partnership |  |  |  | Governance and Operations |  |  |  | Assets and Building
| Invitation and Welcome |  |  | Justice and Community Partnership |  |  | Assets and Building
GOAL | 2021-11-21 | 2021-12-21 | 2021-01-22 | 2021-02-22 | 2021-03-22 | 2021-04-22 | 2021-05-22 | 2021-06-22 | 2021-07-22 | 2021-08-22 | 2021-09-22 | 2021-10-22 | 2021-11-22 | 2021-12-22 | 2021-01-23 | 2021-02-23 | 2021-03-23 | 2021-04-23 | 2021-05-23 | 2021-06-23 | 2021-07-23 | 2021-08-23 | 2021-09-23 | 2021-10-23 | 2021-11-23 | 2021-12-23
Create a model of shared ownership of community life that invites full participation and affirmation of each person.
Create a culture of inclusion through congregational initiatives and actions.
Update the governance and leadership structure of congregation to be more mission-driven. | bar: 2021-01-22 to 2021-04-22
Create a Worship Visioning team for the purpose of exploring and deepening the worship experience and growing/adapting our practice. | bar: 2021-01-22 to 2021-08-22
Identify our mission field and target audiences and develop strategy for reaching and inviting them. | bar: 2021-01-22 to 2021-05-22
Evaluate the long-term financial sustainability of the congregation in the current model and investigate additional revenue streams. | bar: 2021-01-22 to 2021-08-22
Finalize the Mission Endowment Fund bylaws, goals, and structures. | bar: 2021-01-22 to 2021-09-22
Create opportunities and spaces for individuals in the 3rd age to explore God’s love and calling in their current stage of life.
Establish a clear and participatory process for philanthropic giving to the community. | bar: 2021-01-22 to 2021-09-22
Create an annual projected building and grounds maintenance calendar. | bar: 2021-02-22; 2021-10-22
Examine and reform exclusive worship language and practices. | bar: 2021-02-22 to 2021-05-22
Implement the new audio and video equipment for use in worship and equip members to participate in its use. | bar: 2021-03-22 to 2021-04-22
Investigate methods of digital worship and congregational gathering and develop and execute a strategy for greater presence and connection in the community. | bar: 2021-03-22 to 2021-08-22
Establish a new member and visitor pathway. | bar: 2021-05-22 to 2021-08-22
Form a Building Visioning group to complete building audit and identify possible future needs and opportunities that align with our mission. | bar: 2021-05-22 to 2021-12-22
Establish a relevant presence in our community through attending community gatherings and being responsive to community needs. | bar: 2021-07-22 to 2021-12-22
Evaluate operating, staffing, and financial processes and structures and make necessary changes to ensure effectiveness, sustainability, and mission-alignment. | bar: 2021-07-22 to 2021-12-22
Develop an intentional and mission-aligned culture of generosity in the congregation. | bar: 2021-07-22 to 2021-12-22
Train volunteers and implement a home communion ministry to strengthen connection with those that are homebound. | bar: 2021-08-22 to 2021-11-22
Create a culture where families are actively involved in children’s faith formation. | bar: 2021-09-22 to 2021-12-22
Develop a racial justice statement that is affirmed by the congregation and guides Vista’s actions. | bar: 2021-09-22 to 2021-10-22
Provide hands-on faith forming experiences outside the walls of Vista through regular service/immersive learning opportunities and always with a lens of accompaniment. | bar: 2021-11-22 to 2021-12-22
Create adult small group ministries to facilitate deeper relationships and faithful exploration of God, others, and self.
Provide regular public learning opportunities for exploring how God calls us to live in the world.
Discern congregational passions, identify relevant community needs, and engage in issue advocacy.
Develop and execute a strategy and framework for building equitable partnerships with community organizations and groups.